## Tab 1
PROJECT SCHEDULE (SAMPLE)
Project Title:
STRIDE Project No.: | [19 empty] | Year |  |  | Month
Principal Investigator:
Year | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022
Quarter | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | ESTIMATED % COMPLETION PER TASK
Months | Jan-Mar | Apr-Jun | JulAug | Sept-Dec | Jan-Mar | Apr-Jun | JulAug | Sept-Dec | Jan-Mar | Apr-Jun | JulAug | Sept-Dec | Jan-Mar | Apr-Jun | JulAug | Sept-Dec | Jan-Mar | Apr-Jun | JulAug | Sept-Dec | Jan-Mar | Apr-Jun | JulAug | Sept-Dec
RESEARCH TASK
Task 1 - Name of Task
Name of Lead Researcher on this Task |  |  | 10 | 25 | 45 | 75 | 100
Task 2- Name of Task
Name of Lead Researcher on this Task |  |  |  |  | 25 | 50 | 75 | 100
Task 3 - Name of Task
Name of Lead Researcher on this Task |  |  |  | 10 | 20 | 30 | 50 | 60 | 80 | 90 | 100
Task 4 - Final Report
Name of Lead Researcher on this Task | [11 empty] | 50 | 75 | 100
Task 5 - Webinar
Name of Lead Researcher on this Task | [13 empty] | 100
Task 6 - Name of Task
Name of Lead Researcher on this Task
Task 7 - Name of Task
Name of Lead Researcher on this Task
Task 8 - Name of Task
Name of Lead Researcher on this Task
Task 9 - Name of Task
Name of Lead Researcher on this Task
Task 10 - Name of Task
Name of Lead Researcher on this Task
Overall % Complete Projected | 5% | 8% | 15% | 20% | 50% | 55% | 65% | 70% | 80% | 90% | 95% | 100%
Overall % Complete Actual
Green = Pull from Project Timeline found in your Proposal (Doesn't change from QR to QR)
Blue = Update Quarterly
Shade in cells with another color showing where there is an extension of the original deadline (we have shaded orange as an example)
For each new quarterly report, estimate the % of completion for the tasks and entire project to-date
**Percentages shown are examples**